## d3
Finding ID | Finding | DFS 504 Alignment | Detailed Description | Regulatory and Operational Impact | Detailed Supporting Evidence | Remediation Task | TM Feedback | Sanctions Feedback | CRR Feedback | IT / DG Feedback | Supporting Evidence / DFS 504 Basis for Pushback
GL-01 | No consolidated end-to-end AML/OFAC data lineage view | 504.3(a)(5), 504.3(b)(3), 504.3(c)(1)-(3) | The documents describe individual systems, risk assessments, governance processes, and reconciliations, but do not provide one integrated lineage view showing how data moves from source systems through extraction, transformation, Prime/PCS transaction monitoring, FircoSoft filtering, alert generation, case management, escalation, and final regulatory reporting. | CCBNY may be unable to demonstrate that all relevant transactions, customers, counterparties, and payment messages are captured and processed through AML/sanctions controls. This weakens certification defensibility. | AML and OFAC risk assessments describe risks and controls, but not full lineage. Data Governance Policy defines lineage concepts but not actual flows. Change methodology includes system landscape but not field-level lineage. Model Governance Guide discusses Prime, FircoSoft, RegTechOne, reconciliations, and model controls, but does not consolidate them into one DFS 504 lineage artifact. | Develop a DFS 504 specific end to end AML/OFAC data lineage inventory and diagram set covering all in scope systems, interfaces, transformations, controls, reconciliations, owners, and evidence locations. | Under Vendor's Project Understanding & Methodology document - Page 21 - The following is included under Scope of Work: Develop and document end-to-end lineage maps supporting Transaction Monitoring and Filtering, with a focus on NYS DFS Part 504.3 compliance. Vendor included under Key Deliverables: Documented validation methodology, lineage maps, test procedures, findings, and limitations. ***Will these highlighted project deliverables be provided by J.S. Held? Will they be a starting document for the documented lineage inventory and diagram remediation tasks? | 18 | 18 | 18 | Support for pushback: The initial finding is supported because the reviewed documents collectively identify major AML/OFAC systems and processes, but do not provide one integrated, approved end-to-end lineage artifact across source systems, data extraction/loading, transformations, Prime Compliance Suite transaction monitoring, FircoSoft filtering, alert/case disposition, and regulatory outputs. Key sources: annual bsa assessment(1).pdf; ofac annual risk assessment.pdf; changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf; data governance policy.pdf. DFS basis: 3 NYCRR 504.3(a)(5) requires end-to-end testing of the Transaction Monitoring Program, including governance, data mapping, transaction coding, detection scenario logic, model validation, data input and program output; 504.3(b)(3) requires filtering-program testing including data mapping, watch-list matching logic, model validation, data input and program output; 504.3(c)(1)-(3) requires identification of all relevant data sources, validation of data integrity/accuracy/quality, and complete/accurate extraction and loading. Therefore, feedback that lineage is part of the vendor/project scope does not close the finding; it confirms the deliverable is still needed.
GL-02 | Field-level Critical Data Element lineage is incomplete | 504.3(c)(1)-(3), 504.3(a)(5), 504.3(b)(3) | The documentation references CDEs/KDEs, but does not provide a complete DFS 504-specific inventory of fields used in TM, filtering, and CRR, such as customer name, account number, originator, beneficiary, BIC, country, transaction amount, currency, product code, alert ID, case ID, disposition, and SAR/OFAC reporting indicators. | Without field-level lineage, Compliance cannot prove that critical AML/OFAC data elements are sourced correctly, transformed accurately, and consumed appropriately by rules, scenarios, alerts, and reports. | Data Governance Policy defines CDE/KDE concepts. Model Governance Guide references CDEs/KDEs and model workbooks, but actual field-level lineage inventory is not included in the reviewed materials. | Create a DFS 504 CDE inventory documenting business definitions, technical fields, source systems, transformations, downstream usage, controls, owners, and evidence repositories. | Disagree with some of the information under Detailed Description, Detailed Supporting Evidence, and verbiage ("Create") used in Remediation Task. Yes, the CDE, KDE, and ODE list continuously needs to be updated… but this information is already included for TM and Filtering in the following documents that should be updated: 1.) Consolidated Workbooks 2.) DQ Reports BRDs 3.) Data Dictionaries 4.) CCBNY Metadata List 5.) Other TM Documentation 6.) Other Data Governance Documentation | 18 | 18 | 18 | Support for pushback: The finding is not that CDE/KDE concepts do not exist; it is that the reviewed documentation does not evidence a complete DFS 504 field-level lineage inventory connecting each critical field to source system, source field, transformation, target field, downstream usage, control owner, validation rule, and evidence location. Key sources: data governance policy.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(1)-(3) requires identification of all relevant data sources, validation of integrity/accuracy/quality, and complete/accurate extraction/loading; 504.3(a)(5) and 504.3(b)(3) require data mapping and data input/program output testing for TM and filtering. Existing CDE lists, BRDs, dictionaries, or workbooks may be mitigating evidence, but the finding remains open until they are provided and shown to create complete field-level DFS 504 traceability.
GL-03 | Authoritative source systems are not clearly assigned | 504.3(c)(1)-(3), 504.3(c)(4) | Multiple systems are referenced, including New Gen, Prime/PCS, RegTechOne, FircoSoft Trust, FircoSoft Continuity, SWIFT, Fedwire, NISS, GMPS, and reporting platforms, but the documents do not consistently identify the system of record for each critical field. | Inconsistent source ownership increases the risk that downstream monitoring or screening systems rely on stale, duplicated, or conflicting data. | The Model Governance Guide describes multiple systems and reconciliations, while the risk assessments describe systems and control activity. However, no system-of-record matrix is provided. | Establish and govern a DFS 504 system of record matrix by data domain, with formal approval and change impact requirements. | Disagree with the term "Establish" under the Remediation Task… as this already exists and it conflicts with the Detailed Description: "does not consistency identify...". For TM… the source systems are clearly assigned within the PCS Mapping Specifications document and is covered in the consolidated workbook and other CCBNY TM documentation. Refer To Worksheets: 1. ) PCS Mappings Specifications 2.) Activity Name to Product Map 3.) Systems Overview Diagram 4.) PCS Mappings Data Flow Diagrams 5.) TM Rules Thresholds & Settings 6.) Data Governance Documents 7.) Other TM Documents | 18 | 18 | 18 | Support for pushback: The initial finding is supported because source systems may be referenced in PCS mappings or workbooks, but the reviewed documentation does not demonstrate an enterprise-wide system-of-record matrix for all DFS 504-relevant data domains across TM, filtering, sanctions screening, CRR, payment messages, alerts, cases, and reporting. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf; annual bsa assessment(1).pdf; ofac annual risk assessment.pdf. DFS basis: 3 NYCRR 504.3(c)(1) requires identification of all data sources containing relevant data, and 504.3(c)(2)-(3) requires validation and complete/accurate transfer of data from source to automated systems. If PCS mapping covers TM, the response may partially mitigate TM scope, but it does not close the broader authoritative-source finding without cross-system source-of-record governance.
GL-04 | Transformation and mapping logic is not sufficiently transparent | 504.3(a)(5)-(6), 504.3(b)(3)-(4), 504.3(c)(2)-(3) | The documentation references mapping specifications, data dictionary updates, model rules, tuning, filtering logic, and Prime activity imports, but does not provide complete source-to-target mapping logic or transformation rules for AML/OFAC data flows. | Mapping errors, truncation, parsing issues, country-code issues, suppression logic, or enrichment errors could impair monitoring/filtering outcomes and remain undetected. | Change Management document describes testing and change categories. Model Governance Guide references data mapping specifications and data dictionary controls, but detailed transformation rules are not included in the reviewed evidence. | Document field level source to target mappings and transformations and incorporate mapping validation into testing and model governance. | Agree and disagree with some of the information under Detailed Description. For TM, some of this is available / covered in the consolidated workbook and other CCBNY TM documentation. Refer To Worksheets: 1. ) PCS Mappings Specifications 2.) Activity Name to Product Map 3.) Systems Overview Diagram 4.) PCS Mappings Data Flow Diagrams 5.) TM Rules Thresholds & Settings 6.) Data Governance Documents 7.) Other TM Documents | 18 | 18 | 18 | Support for pushback: The finding is supported because the documentation references mapping specifications, data dictionaries, and change/testing controls, but does not include complete and reviewable transformation logic across relevant AML/OFAC flows. Key sources: changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(5)-(6) requires data mapping, scenario logic, model validation, data input/output testing, and documentation of scenarios, assumptions, parameters, and thresholds; 504.3(b)(3)-(4) similarly requires filtering-program data mapping and documentation of tools, processes, or technology; 504.3(c)(2)-(3) requires validation that accurate and complete data flows through the programs. Client feedback that “some” logic exists supports a partial-mitigation position, not closure, unless complete mappings and transformation rules are provided.
GL-05 | Reconciliation coverage is fragmented and not enterprise-wide | 504.3(c)(2)-(3), 504.3(a)(5), 504.3(b)(3) | Prime/PCS reconciliation procedures are described in detail, but comparable reconciliation evidence is not clearly documented for FircoSoft, sanctions list feeds, SWIFT/Fedwire, NISS, GMPS, BIC screening, vendor/employee screening, batch screening, alerts, cases, and regulatory outputs. | CCBNY may be able to evidence completeness for selected Prime feeds, but not for the entire transaction monitoring and filtering ecosystem. | Model Governance Guide includes customer, account, and activity reconciliation procedures for Prime/PCS. OFAC assessment describes screening processes, but does not evidence equivalent source-to-target reconciliation across all sanctions populations. | Implement an enterprise DFS 504 reconciliation framework covering all AML/OFAC data populations. | Disagree with 504.3(a)(5) in that all TM supporting documentation requested by Vendor was provided and includes clear documented evidence of the following: 1.) Governance 2.) Data Mapping 3.) Transaction Coding 4.) Detection Scenario Logic (***Rules, Recon, & UAT/V) 5.) Model Validation 6.) Data Input & Output If additional evidence or something else is needed, please submit request via email. | 18 | 18 | 18 | Support for pushback: The finding is supported because the reviewed evidence shows Prime/PCS reconciliation procedures, but does not show equivalent end-to-end reconciliation coverage across the full AML/OFAC ecosystem, including FircoSoft, SWIFT/Fedwire, NISS/GMPS, batch screening, BIC screening, vendor/employee screening, alerts, cases, and regulatory outputs. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf; ofac annual risk assessment.pdf. DFS basis: 3 NYCRR 504.3(c)(2)-(3) requires validation of data integrity/accuracy/quality and complete/accurate extraction/loading; 504.3(a)(5) and 504.3(b)(3) support data-input and program-output testing. If TM documentation supports selected Prime feeds, the finding can be scoped as partially mitigated for TM but remains open for enterprise AML/OFAC coverage.
GL-06 | Manual reconciliations and manual screening workarounds create sustainability risk | 504.3(c)(2)-(4), 504.3(d) | Several processes rely on manual logs, spreadsheet comparisons, manual count entry, manual investigation, manual routing, and manual screening or workaround activity. | Manual processes increase the risk of missed records, inconsistent execution, delayed review, weak auditability, and evidence gaps. | Model Governance Guide includes manual reconciliation steps such as reviewing logs and comparing spreadsheet values. OFAC documentation identifies manual or operational screening/control activities. | Standardize manual controls, implement maker checker review, execution logs, QA sampling, and define automation roadmaps. | The manual TM reconciliations and controls are standardized and documented. Recommend to provided QA and QC supporting documentation to Vendor. | 18 | 18 | 18 | Support for pushback: The finding remains supportable because standardized manual reconciliations and controls still present sustainability risk unless execution evidence shows consistent maker-checker review, timestamps, control totals, exceptions, QA/QC, escalation, and periodic independent review. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf; ofac annual risk assessment.pdf. DFS basis: 3 NYCRR 504.3(c)(2)-(4) requires data integrity validation, complete/accurate data transfer, and governance/management oversight, including policies and procedures ensuring changes and controls are defined, managed, controlled, reported, and audited; 504.3(d) requires documentation of material improvement efforts. Documentation that manual controls are standardized is mitigating, but not sufficient to eliminate manual-process risk without operating evidence.
GL-07 | Data completeness controls are not fully evidenced | 504.3(c)(1)-(3), 504.3(a)(5), 504.3(b)(3) | The documents describe reconciliation and data quality concepts, but do not provide a complete evidence package proving that all relevant customers, accounts, transactions, counterparties, payment messages, alerts, and reporting outputs are captured. | The Branch may be challenged on whether all relevant activity is monitored and screened, especially where systems, feeds, or manual workarounds are not reconciled end-to-end. | AML/OFAC assessments provide program context; Model Governance Guide provides selected reconciliation procedures; Data Governance Policy states completeness principles. Together, they do not evidence full population completeness. | Implement population level completeness controls and dashboards with escalation thresholds. | Disagree with 504.3(a)(5) in that all TM supporting documentation requested by Vendor was provided and includes clear documented evidence of the following: 1.) Governance 2.) Data Mapping 3.) Transaction Coding 4.) Detection Scenario Logic (***Rules, Recon, & UAT/UAV) 5.) Model Validation 6.) Data Input & Output | 18 | 18 | 18 | Support for pushback: The finding is supported because the reviewed documents describe reconciliation and data quality concepts but do not provide a complete population-level evidence package proving that all relevant customers, accounts, transactions, payment messages, alerts, cases, and reports are captured. Key sources: annual bsa assessment(1).pdf; ofac annual risk assessment.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(1)-(3) requires relevant data source identification and complete/accurate data flows; 504.3(a)(5) and 504.3(b)(3) require data input and program output testing. Feedback that TM support was provided should be validated against specific samples, but the finding remains open until completeness evidence is traceable by population and feed.
GL-08 | Data accuracy controls are not sufficiently evidenced | 504.3(c)(2), 504.3(a)(5), 504.3(b)(3) | The documents discuss data quality and model effectiveness, but do not provide robust evidence of accuracy testing for customer attributes, beneficial ownership, geography, industry, product, BIC, transaction amount, currency, counterparty data, or alert dispositions. | Inaccurate data can result in false negatives, false positives, incorrect customer risk ratings, missed sanctions hits, or incomplete SAR/OFAC decisioning. | Data Governance Policy defines accuracy as a guiding principle. Model Governance Guide references data quality and model validation, but does not provide comprehensive CDE accuracy testing results. | Implement periodic accuracy testing and profiling for DFS 504 CDEs. | Remediation Task should be more specific. Currently for TM, the periodic accuracy testing and profiling in relationship to items in the Detailed Description already exists to some degree. References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf. Note: Please refer to Email Approval From Paul So on 04/13/2026 To Share DGO Documents: RE: Internal Request For Approval To Share Bookmarked Confidential DGO Documents With Data Lineage Vendor - J.S. Held LLC.msg. The Remediation Task does not reflect the Detailed Supporting Evidence provided. Should state update the Data Governance Policy and Model Governance Guide documents to reflect the successful completion of accuracy testing and profiling for DFS 504 CDEs and KDEs that has occurred quarterly since the 4th Quarter 2022. Evidence and supporting documents were provided in the following: 1.) BRD - TM DQ Report - Version 1.1 - 03302026 - MH.docx and 2.) In all 12 CCBNY Data Quality Report TM Responses provided. The location of the evidence of the accuracy testing for customer attributes, beneficial ownership, geography, industry, product, BIC, transaction amount, currency, counterparty data, and alert dispositions... should be requested / discussed as they all exist and are done daily, weekly, monthly, and/or quarterly. | 18 | 18 | 18 | Support for pushback: The finding should remain pending validation because the feedback indicates quarterly accuracy testing and DQ reports may exist, but those artifacts were not clearly evidenced in the reviewed documentation and must be tied to DFS 504 CDEs/KDEs, source systems, thresholds, exceptions, and remediation. Key sources: data governance policy.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(2) requires validation of data integrity, accuracy, and quality to ensure accurate and complete data flows; 504.3(a)(5) and 504.3(b)(3) require data input/program output testing. If the BRD and DQ reports substantiate periodic accuracy testing, the finding can be downgraded or revised, but not closed without evidence review.
GL-09 | Data quality metrics and thresholds are underdeveloped | 504.3(c)(2), 504.3(c)(4), 504.3(d) | Data quality is discussed conceptually, but the documents do not define a DFS 504 scorecard with measurable thresholds for completeness, accuracy, timeliness, validity, duplicates, rejects, missing mandatory fields, stale records, failed interfaces, or aged exceptions. | Governance may lack objective criteria to determine when data quality is acceptable, deteriorating, or requiring escalation/remediation. | Data Governance Policy and DGC Charter reference data quality, metrics, dashboards, and corrective action, but do not define DFS 504-specific scorecards or thresholds. | Define DFS 504 data quality metrics, thresholds, and escalation paths. | References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding remains supportable because the Data Governance Policy and DGC Charter establish broad data quality governance, but the reviewed evidence does not define a DFS 504-specific data quality scorecard with metrics, thresholds, tolerance levels, breach escalation, and reporting cadence for TM/filtering data. Key sources: data governance policy.pdf; data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(c)(2) requires validation of data integrity, accuracy, and quality; 504.3(c)(4) requires governance and management oversight; 504.3(d) requires documentation of material improvement/update/redesign areas. General policy references are design evidence, not operating metrics.
GL-10 | Exception management is not mature enough for DFS 504 | 504.3(c)(4), 504.3(d) | Escalation and issue tracking are described, but the documents do not provide a centralized DFS 504 data issue log with severity, owner, root cause, due date, aging, compensating controls, closure evidence, and independent validation. | Data issues may be identified but not consistently tracked, trended, escalated, remediated, or evidenced for certification. | Data Governance Policy references issue management. DGC Charter references escalation. Model Governance Guide identifies high-priority data migration/integration issues but does not provide a consolidated issue lifecycle artifact. | Implement a centralized DFS 504 data issue log with independent closure validation. | References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because policies and charters describe issue management and escalation, but the reviewed set does not include a DFS 504 issue log with severity, root cause, owner, aging, compensating controls, closure evidence, and independent validation. Key sources: data governance policy.pdf; data governance committee charter.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight, including controlled, reported, and audited changes; 504.3(d) requires documentation of identified material improvement areas and remediation efforts. Policy references alone do not prove issues are being managed through closure.
GL-11 | Change management is not consistently lineage-driven | 504.3(c)(4), 504.3(a)(5), 504.3(b)(3), 504.3(d) | The Change Management document establishes testing/change-control processes, but does not consistently require a DFS 504 lineage impact assessment for system, rule, mapping, threshold, sanctions-list, vendor, or source-data changes. | Small technical changes could unintentionally disrupt monitoring/filtering data flows, impair rules, or create undetected data integrity breaks. | Change Management document defines SDLC/STLC, change categories, testing types, and approvals. Model Governance Guide references system/model changes, but there is no mandatory DFS 504 lineage impact checklist in the reviewed evidence. | Embed DFS 504 lineage impact analysis into change management. | Agreed. | 18 | 18 | 18 | Support for pushback: The client agreed, and the finding is supported by the reviewed documents because change management controls exist but are not consistently framed around DFS 504 lineage impact for changes to feeds, mappings, scenarios, thresholds, systems, sanctions lists, or source data. Key sources: changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight, including policies and procedures governing changes to the TM/filtering program so changes are defined, managed, controlled, reported, and audited; 504.3(a)(5) and 504.3(b)(3) require testing including data mapping and data input/program output.
GL-12 | Testing is functional but not sufficiently lineage-focused | 504.3(a)(5), 504.3(b)(3), 504.3(c)(2)-(3) | UAT, regression, parallel testing, ATL/BTL testing, tuning, and validation are described, but testing is not consistently framed around proving full-population completeness, source-to-target accuracy, field mapping, rejects, exclusions, and downstream outputs. | Functional testing may confirm that systems operate, but may not detect missing records, mapping defects, or excluded populations. | Change Management document describes testing methodologies. Model Governance Guide describes tuning, validation, and testing, but not a comprehensive lineage-based testing framework. | Develop DFS 504 lineage based test cases. | Some of the statements provided are generic / general and require additional details and specifications. Not all testing requires lineage testing and/or lineage test cases. Discuss with Vendor as all testing that requires verification of data flows from source to destination, including all transformations, ensuring success are completed based on the type of test being completed and the results of the Reconciliation Report as a linage based test case as well as all other specified / required applicable lineage test cases. The ISO Testing document provided elaborates on when it was and was not done. | 18 | 18 | 18 | Support for pushback: The response is partially valid that not every test must be lineage testing; however, DFS 504-relevant changes and controls should include lineage-based testing where data flows, mappings, populations, rules, or outputs are affected. Key sources: changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(5) requires end-to-end pre/post implementation testing of TM including data mapping, data input, and program output; 504.3(b)(3) requires similar testing for filtering; 504.3(c)(2)-(3) requires validation of data integrity and complete/accurate extraction/loading. Reconciliation reports may be one form of lineage testing but do not replace a defined testing framework.
GL-13 | Vendor and third-party lineage is not fully governed | 504.3(c)(5), 504.3(b)(3), 504.3(c)(2) | FircoSoft, RegTechOne, LexisNexis-related tools, and third-party validators are referenced, but vendor input/output data flows, processing logic, SLAs, exceptions, and independent validations are not fully mapped. | Vendor tools may operate as “black boxes,” weakening the Branch’s ability to prove completeness, accuracy, and processing integrity. | OFAC and Model Governance documents reference FircoSoft/Firco Continuity, RegTechOne, vendor selection, and validation, but do not provide complete vendor data lineage artifacts. | Document vendor lineage and require independent validation. | Vendor recommendation is related to KYC and Sanctions. Note: I was sure from prior KYC and OFAC consolidated workbook development, that some of this information described under Detailed Description was available / present. ***Recommend to review and provide references if available and to add / include them or add the location of them within the OFAC and KYC Model Governance documents. | 18 | 18 | 18 | Support for pushback: The finding remains open because the feedback indicates this may relate to KYC/Sanctions and additional evidence may exist, but the reviewed documentation does not include complete vendor data lineage, input/output validation, SLAs, list-update controls, or vendor-processing transparency. Key sources: ofac annual risk assessment.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(5) requires a vendor selection process if a third-party vendor is used to acquire, install, implement, or test the program or any aspect of it; 504.3(b)(3) and 504.3(c)(2) require filtering testing and validation of data integrity/quality. Vendor use does not remove institutional accountability.
GL-14 | Alert-to-case-to-reporting lineage is underdeveloped | 504.3(a)(7), 504.3(b)(3), 504.3(c)(2)-(3) | The documentation discusses alerts, cases, SARs, OFAC reporting, dispositions, and escalation, but does not provide a traceable path from source data to alert, case, decision, filing, or no-file rationale. | The Branch may not be able to prove that all alerts were investigated, all cases were dispositioned, and all reportable events were appropriately escalated or reported. | AML/OFAC risk assessments and Model Governance Guide describe alerts, cases, SAR/OFAC processes, and reviews, but do not provide downstream lineage from source transaction/customer record to regulatory output. | Develop alert to reporting lineage documentation and reconciliations. | Shouldn't the remediation task state Develop Alert-to-Case-to Reporting… like I the Finding? There are controls in place for the Alerts and Cases Statuses from an AML / TM perspective. This was provided in the 9.4B - Frequently Submitted Alerts and Cases Metrics - April 3, 2026.msg Recommend to request CCBNY SAR Representative and applicable Case / SAR documentation and to provide applicable DC and DQ documentation. The Model Governance Guide is a guide that includes KPI processes and provides multiple references to the location for decisioning, filing, and no-filing rationales: (AML Desktop Procedure, Rationale Documents, CCBNY Consolidated PCS Rules Specifications Workbook, etc.). Note: The Risk Assessment & Model Gov Guides are not meant to include / provide downstream lineage from source transaction / customer record, to regulatory output. There should be a separate lineage document that should be referenced in the guide. | 18 | 18 | 18 | Support for pushback: The finding is supported because alert/case metrics are not the same as lineage from source transaction/customer record to alert, case, investigator disposition, escalation, SAR/OFAC outcome, and no-file rationale. Key sources: annual bsa assessment(1).pdf; ofac annual risk assessment.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(7) requires protocols for alert investigation, filing/action decisions, responsible parties, and documentation of investigative and decision-making processes; 504.3(b)(3) and 504.3(c)(2)-(3) support output traceability and data integrity validation. If downstream lineage belongs in another document, it should be provided and cross-referenced.
GL-15 | Manual overrides and risk adjustments need stronger governance | 504.3(a)(5), 504.3(c)(2), 504.3(c)(4) | CRR manual adjustments and compliance overrides are permitted and described, but the documents do not evidence systematic trend analysis, independent review, pattern monitoring, or periodic validation of override appropriateness. | Overrides may mask data quality issues, distort risk scores, or create inconsistent customer risk treatment. | Model Governance Guide describes CRR manual adjustments and compliance overrides, including rationale and approval expectations, but does not evidence independent analytics or periodic pattern review. | Implement override analytics, governance review, and escalation triggers. | Vendor recommendation is related to KYC - CRR Overrides documented in the Model Governance Guide. Note 1: CRR information / evidence was not provided because it is not in scope. If needed, I am sure it can be provided. Note 2: The Model Governance Guide is not meant to documents evidence of systematic trend analysis, independent reviews, pattern monitoring and reviews, and/or periodic validation of override appropriateness. See Section 5.2 - Objective / Purpose. Should be in workbook. If needed, there should be a separate lineage document managed by the DGO that can include this evidence and should be referenced in the guide as per Compliance Model Governance Function: China Construction Bank – New York Branch, has established a Data Governance Function and designated an Officer responsible for identifying and overseeing the data lineage risks associated with systems and processes utilized by CCBNY, and implementing controls designed to ensure the integrity of data, migrated throughout the Bank’s systems. | 18 | 18 | 18 | Support for pushback: If CRR is outside the current TM scope, the finding can be scoped as CRR-specific; however, it is not remediated by stating it is outside TM. The reviewed Model Governance Guide permits CRR manual adjustments/overrides but does not evidence systematic override analytics or independent pattern review. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(5) requires review of governance, model validation, data input and program output for TM; 504.3(c)(2) requires validation of data accuracy/quality; 504.3(c)(4) requires governance oversight. Overrides affecting risk outputs require controlled documentation and review.
GL-16 | Governance exists, but operating evidence is insufficient | 504.3(c)(4), 504.3(d), 504.4 certification support | The DGC Charter, Data Governance Policy, and Model Governance Guide establish governance structures, but the reviewed documentation does not include actual DGC minutes, decision logs, issue reports, data quality dashboards, approval records, or closure evidence. | Policies and charters evidence design, but not operating effectiveness. Certification support may be weak if governance execution cannot be demonstrated. | DGC Charter defines meetings, recordkeeping, escalation, and committee responsibilities. Data Governance Policy and Model Governance Guide define governance roles. Actual governance execution evidence was not included. | Maintain a DFS 504 governance evidence package. | References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Note: The Model Governance Guide is not meant to include actual DGC minutes, decision logs, issue reports, data quality dashboards, approval records, or closure evidence. See Section 5.2 - Objective / Purpose. Should be in workbooks or separate DFS 504 package that is managed by DGO and includes this information and it then can / should be referenced in the Model Governance guide. | 18 | 18 | 18 | Support for pushback: The client feedback supports the finding rather than refutes it: if minutes, issue logs, and approvals belong in a separate DFS 504 package, then they must be provided and linked to the finding evidence. Key sources: data governance committee charter.pdf; data governance policy.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight; 504.3(d) requires documentation of material improvement efforts; 504.4 requires maintenance of records, schedules, and data supporting the annual board resolution/senior officer compliance finding. Governance design does not prove operating effectiveness.
GL-17 | DGC Charter is not explicitly DFS 504-specific | 504.3(c)(4), 504.3(d) | The DGC Charter establishes general data governance oversight, but does not explicitly assign responsibility for DFS 504 lineage, transaction monitoring data integrity, filtering data integrity, certification evidence, or review of DFS 504-specific metrics. | The DGC could operate effectively for general data governance while not consistently overseeing DFS 504-specific lineage risks. | DGC Charter defines broad data responsibilities and escalation, but lacks explicit DFS 504 lineage agenda requirements and metrics. | Update the DGC Charter to include DFS 504 lineage oversight. | References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Note: The DGC Charter provided was the latest submitted to Data Stewards (10/29/2024). There was an updated copy submitted for Data Owner Vote on 02/05/2025; however, the final / approved copy was never shared / distributed by DGO to Data Stewards. | 18 | 18 | 18 | Support for pushback: The finding remains supportable because the DGC Charter reviewed provides general data governance oversight but does not explicitly assign DFS 504 lineage oversight or recurring review of TM/filtering data integrity metrics. If a newer charter exists, it must be provided for review. Key source: data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight over the TM/filtering program and changes; 504.3(d) requires documented remediation efforts. General DGC oversight does not necessarily evidence DFS 504-specific oversight.
GL-18 | Governance cadence may be insufficient for active data integrity issues | 504.3(c)(4), 504.3(d) | The DGC Charter establishes quarterly meetings with special sessions as needed, but DFS 504 lineage remediation and high-risk breaks may require more frequent review. | Critical issues such as failed feeds, missed files, mapping defects, and unresolved reconciliation breaks may not receive timely senior oversight. | DGC Charter defines meeting cadence and escalation. No DFS 504-specific monthly reporting cadence is established. | Implement monthly DFS 504 data integrity reporting. | Under Regulatory and Operational Impact: Instead of "may not receive timely senior oversight."... should state 'may not receive timely DGO / senior management oversight.'. References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Please refer to the CCO - Mildred Harper provided feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: Wording can be refined to reference DGO/senior management oversight, but the issue remains whether quarterly or general governance cadence is sufficient for active DFS 504 data integrity risks such as failed feeds, reconciliation breaks, or mapping defects. Key source: data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight; 504.3(d) requires documentation of identified material improvements and remedial efforts. Timely escalation is essential for regulatory defensibility.
GL-19 | No unified DFS 504 certification evidence framework | 504.3(a)-(d), 504.4 | The documents reference DFS 504, model governance, budgeting, validation, data governance, and controls, but do not define a consolidated certification evidence package mapped to DFS 504.3 requirements. | Senior officer or board certification may lack a structured evidence basis. DFS notes certification is required annually and must be submitted even where material improvement areas are documented. ([Department of Financial Services][2]) | Model Governance Guide references DFS 504 budgeting and compliance model governance. DGC Charter and Data Governance Policy support governance, but no DFS 504 control/evidence matrix is provided. | Develop a DFS 504 certification control matrix and evidence binder. | Note: There were refined DFS 504 Certification Framework documents managed by Yacoub Soumahoro - Monitoring and Testing Manager which included DFS Part 504 Key Documents / Framework: 1.) Kick-Off Meeting Deck - 2.) Certificate Control Matrix / Tracking Workbook 3.) Monthly Summary Updates - DFS Part 504 Summaries. Recommendation 1: Provide all applicable DFS 504 documents to Vendor. I only provided what was requested by Vendor in the request list: Latest DFS Part 504 Annual Certification. Recommendation 2: Create new Compliance SharePoint folder and include all 504 documents on the Intranet. This will be the official 504 evidence binder and the log will be the official control matrix. | 18 | 18 | 18 | Support for pushback: The feedback is potentially mitigating but not closing unless the alleged DFS 504 Certification Framework documents, evidence matrices, and monthly summaries are provided and reviewed. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf; data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(a)-(d) sets TM/filtering program requirements, and 504.4 requires adoption/submission of a board resolution or senior officer compliance finding and maintenance of supporting records, schedules, and data for five years. The finding should be marked open pending evidence review.
GL-20 | Enterprise AML/OFAC architecture inventory is incomplete | 504.3(c)(1), 504.3(c)(3), 504.3(c)(4) | The Change Management document includes a systems overview, but no complete architecture inventory ties together systems, interfaces, CDEs, data owners, feed frequency, controls, and DFS 504 relevance. | Incomplete architecture visibility increases the risk that systems, feeds, or dependencies are omitted from lineage, testing, and change impact analysis. | Change Management document contains a systems overview diagram and system categorization. Other documents reference systems individually, but no integrated AML/OFAC data architecture inventory is provided. | Develop and maintain an AML/OFAC architecture and dependency inventory. | Need to discuss integrated AML/OFAC data architecture inventory and dependency inventory with Vendor to get a better understanding of what is actually being requested. Please refer to CCO - Mildred Harper's feedback that was provided at the 05/06/2026 Status Meeting. | 18 | 18 | 18 | Support for pushback: The finding is supported because the current documentation includes a systems overview but not a complete AML/OFAC data architecture inventory with systems, interfaces, data domains, CDEs, owners, feed frequency, controls, and DFS 504 relevance. Key source: changemanagement.pdf. DFS basis: 3 NYCRR 504.3(c)(1) requires identification of all relevant data sources; 504.3(c)(3) requires complete/accurate extraction/loading; 504.3(c)(4) requires governance/management oversight. Requesting clarification does not rebut the gap; it confirms the artifact needs definition.
GL-21 | DFS 504 evidence retention standards are not defined | 504.3(c)(4), 504.3(d), 504.4 | Retention and recordkeeping are referenced generally, but there is no DFS 504-specific retention standard for lineage maps, reconciliations, test results, issue logs, approvals, model validations, and certification support. | Historical evidence may be unavailable or inconsistently retained, reducing examination readiness. | Data Governance Policy addresses data lifecycle/retention broadly. DGC Charter addresses committee recordkeeping. No DFS 504-specific evidence retention schedule is provided. | Define DFS 504 specific evidence retention standards. | The Record Retention and Disposal Policy was not requested by vendor - Not in list of 62 requested items. The latest version can / should be provided: CCBNY Record Retention and Disposal Policy 02262026 - FINAL.pdf. It however, only references 500.06 and 500.13. | 18 | 18 | 18 | Support for pushback: The finding remains open pending review of the Record Retention and Disposal Policy because the reviewed documents reference recordkeeping generally but do not define DFS 504-specific evidence retention for lineage maps, reconciliations, test results, issue logs, approvals, and certification support. Key sources: data governance policy.pdf; data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(c)(4) and 504.3(d) require governance and documentation of remediation efforts; 504.4 requires supporting records, schedules, and data to be maintained for examination for five years.
GL-22 | Documentation is fragmented across multiple frameworks | 504.3(a)-(d) | Risk assessments, model governance, data governance, committee governance, and change management each contain relevant content, but there is no single DFS 504 lineage playbook consolidating scope, controls, owners, evidence, and testing. | Fragmentation increases reliance on institutional knowledge and makes regulatory review more difficult. | All reviewed documents contain partial support, but no single integrated DFS 504 lineage standard or playbook exists. | Develop a DFS 504 Data Lineage Standard or Playbook. | Recommend to modify the Remediation Task to 'Enhance the' instead of "Develop a". | 18 | 18 | 18 | Support for pushback: The client’s proposed wording change from “develop” to “enhance” may be reasonable, but it does not invalidate the finding. The reviewed documents remain fragmented across AML risk, OFAC risk, data governance, change management, model governance, and DGC governance without a consolidated DFS 504 lineage playbook. Key sources: annual bsa assessment(1).pdf; ofac annual risk assessment.pdf; data governance policy.pdf; changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf; data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(a)-(d) requires an integrated TM/filtering program with testing, data integrity, governance, vendor oversight, qualified personnel, training, and remediation documentation.
GL-23 | Model governance is stronger than underlying data lineage governance | 504.3(a)(5), 504.3(b)(3), 504.3(c)(2)-(3) | The Compliance Model Governance Guide provides robust model governance for CRR, TM, and FP, but does not fully evidence the completeness, accuracy, and traceability of the data feeding those models. | Well-governed models may still fail if input data is incomplete, inaccurate, stale, or incorrectly mapped. | Model Governance Guide provides strong detail on model governance, tuning, validation, and reconciliation, but not complete field-level lineage across all inputs/outputs. | Integrate data lineage reviews into model governance processes. | Please refer to the CCO - Mildred Harper provided feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because the reviewed Model Governance Guide is more mature regarding model governance, tuning, validation, and program controls than regarding complete underlying field-level data lineage across all inputs/outputs. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(5) and 504.3(b)(3) require testing including model validation, data mapping, data input and program output; 504.3(c)(2)-(3) requires data integrity and complete/accurate data flows. Prior CCO feedback should be reviewed, but generalized references do not close the gap.
GL-24 | Sanctions screening population coverage is not fully evidenced | 504.3(b)(1)-(5), 504.3(c)(1)-(3) | The OFAC materials and Model Governance Guide discuss FircoSoft/Firco Continuity, customer screening, transaction screening, and other screening populations, but do not provide a complete coverage matrix for customers, related parties, non-customers, counterparties, vendors, employees, BICs, payment messages, and list updates. | Incomplete screening population coverage could result in missed sanctions exposure or inability to evidence filtering completeness. | OFAC Risk Assessment describes sanctions screening and filtering activities. Model Governance Guide discusses filtering program governance. A complete sanctions population/source/control matrix is not provided. | Develop a sanctions screening population coverage matrix. | All Sanctions related. Please refer to Sanctions Feedback. | 18 | 18 | 18 | Support for pushback: The finding should remain under sanctions scope because the OFAC documentation and Model Governance Guide discuss screening, but the reviewed documents do not provide a complete population coverage matrix for customers, related parties, non-customers, vendors, employees, BICs, payment messages, and list updates. Key sources: ofac annual risk assessment.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(b)(1)-(5) requires a filtering program based on risk assessment with appropriate end-to-end testing and documentation of filtering tools/processes; 504.3(c)(1)-(3) requires source identification and data integrity/transfer controls.
GL-25 | Transaction monitoring scenario lineage is incomplete | 504.3(a)(3)-(8), 504.3(c)(2)-(3) | TM rules and tuning are described, but the documents do not fully map each scenario to source data fields, applicable transaction populations, inclusion/exclusion logic, thresholds, transformations, and alert outputs. | Rules may not be demonstrably aligned to the correct data populations, creating false-negative risk and weakening suspicious activity monitoring. | AML Risk Assessment and Model Governance Guide describe TM program/rules/tuning, but do not provide scenario-level lineage for each rule. | Document scenario level lineage for all TM rules. | Disagree. This is already covered in the consolidated workbook, rules rationales, and other CCBNY TM documentation. Refer To Worksheets: 1. ) PCS Mappings Specifications 2.) Activity Name to Product Map 3.) Systems Overview Diagram 4.) PCS Mappings Data Flow Diagrams 5.) TM Rules Thresholds & Settings 6.) Data Governance Documents If you disagree, please provide an example of what you are looking for in relationship to any one of the PCS Rules and I will show you evidence where the information exists for that rule / scenario. | 18 | 18 | 18 | Support for pushback: The client may have mitigating evidence in consolidated workbooks and rule rationales, but the finding remains open until several representative TM rules are reviewed and shown to include source fields, population, exclusions, thresholds, transformations, scenario logic, alert output, and reconciliation. Key sources: annual bsa assessment(1).pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(3)-(8) requires detection scenarios, thresholds, data mapping, model validation, data input/output testing, scenario documentation, alert protocols, and ongoing scenario analysis; 504.3(c)(2)-(3) requires data integrity and complete/accurate transfer.
GL-26 | Customer Risk Rating lineage is not fully connected to source data and downstream use | 504.3(a)(1), 504.3(a)(3), 504.3(c)(2) | CRR methodology is described in detail, but each CRR input is not fully mapped to source fields, transformations, score calculation, manual adjustments, overrides, and downstream monitoring/reporting usage. | Incorrect CRR inputs can misclassify customers and affect due diligence, monitoring prioritization, and risk reporting. | Model Governance Guide describes RegTechOne, CRR factors, weights, trigger questions, manual adjustments, and overrides, but does not provide full source-to-output lineage. | Build CRR source to output lineage and validate inputs. | Vendor recommendation is related to KYC - CRR Overrides documented in the Model Governance Guide. Note 1: CRR information / evidence was not provided because it is not in scope. If needed, I am sure it can be provided. Note 2: The Model Governance Guide is not meant to documents evidence of systematic trend analysis, independent reviews, pattern monitoring and reviews, and/or periodic validation of override appropriateness. See Section 5.2 - Objective / Purpose. Should be in workbook. If needed, there should be a separate lineage document managed by the DGO that can include this evidence and should be referenced in the guide as per Compliance Model Governance Function: China Construction Bank – New York Branch, has established a Data Governance Function and designated an Officer responsible for identifying and overseeing the data lineage risks associated with systems and processes utilized by CCBNY, and implementing controls designed to ensure the integrity of data, migrated throughout the Bank’s systems. | 18 | 18 | 18 | Support for pushback: If CRR is outside TM scope, the finding can be separated as CRR-specific, but it is not remediated without source-to-output lineage for CRR inputs and downstream usage. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(1) requires TM to be based on the institution’s risk assessment; 504.3(a)(3) requires detection scenarios based on risk; 504.3(c)(2) requires validation of data integrity/accuracy/quality. CRR data can affect risk-based monitoring and due diligence; therefore lineage remains relevant.
GL-27 | Payment screening manual workarounds require stronger compensating controls | 504.3(b)(2)-(3), 504.3(c)(2)-(4), 504.3(d) | Payment screening flows involving SWIFT/Fedwire or non-customer transactions appear to involve manual or special handling in certain circumstances. | Manual payment screening gaps create heightened sanctions risk because interdiction failures may occur before funds move or messages are completed. | OFAC Risk Assessment and Model Governance Guide reference payment screening, FircoSoft filtering, and manual/control procedures, but compensating controls are not fully evidenced. | Formalize compensating controls and track volumes and exceptions. | Youngran Kim to respond. | 18 | 18 | 18 | Support for pushback: No substantive rebuttal has been provided. The finding remains open because payment screening manual workarounds and special handling require documented compensating controls, reconciliation, QA, and escalation. Key sources: ofac annual risk assessment.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(b)(2)-(3) requires filtering based on technology/processes/tools for matching names/accounts and end-to-end filtering testing; 504.3(c)(2)-(4) requires data integrity, complete/accurate transfer, and governance oversight; 504.3(d) requires documentation of improvement efforts.
GL-28 | Independent validation of lineage controls is not clearly required | 504.3(a)(5), 504.3(b)(3), 504.3(c)(4), 504.3(d) | Internal Audit, Risk, Compliance, Data Governance, and third-party reviews are referenced, but there is no explicit independent validation framework for lineage maps, reconciliations, data quality metrics, change impact assessments, and issue closure. | Overreliance on self-assessment may reduce confidence in completeness, accuracy, and remediation effectiveness. | Model Governance Guide references internal audit and third-party validation. Data Governance Policy references governance roles. No dedicated independent data lineage validation standard is provided. | Require periodic independent DFS 504 lineage validation. | Agreed with some, but not all - For Example: 3rd Party Reviews may or may not need independent validation of data lineage or controls as a requirement to successfully complete the deliverables / project(s) that they are assigned to complete. Recommend to reword the Detailed Description to make it applicable. Note 1: For the Data Lineage Vendor Reviews... it is / should be required. Note 2: Isn't this what the Vendor is doing? If so, not sure why it is documented under the Remediation Task. | 18 | 18 | 18 | Support for pushback: The finding should be refined rather than removed. Independent validation may not be required for every activity, but it should be required for material DFS 504 lineage controls, high-risk remediation closures, and material TM/filtering data integrity assertions. Key sources: compliance governance guidepdf.pdf; compliance model gov.pdf; data governance policy.pdf. DFS basis: 3 NYCRR 504.3(a)(5) and 504.3(b)(3) require model validation and testing; 504.3(c)(4) requires governance/management oversight; 504.3(d) requires documented remediation. Vendor assessments may be one form of validation but do not replace independent challenge of institutional controls.
GL-29 | Decision rights over lineage matters are not specific enough | 504.3(c)(4), 504.3(d) | The DGC Charter defines general decisioning and voting, but does not specify which DFS 504 matters require DGC approval, Compliance approval, Risk review, IT approval, or senior management escalation. | Material lineage decisions may be handled inconsistently or at too low a level of governance. | DGC Charter provides general decisioning structure, but does not define DFS 504-specific decision rights for CDEs, mapping changes, high-risk breaks, manual workarounds, or issue closure. | Define DFS 504 lineage decision rights matrix. | References DGO'S DG-01-250 CCBNY Data Governance Policy.pdf and DGC Charter. Please refer to the CCO - Mildred Harper provided feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding remains supported because the DGC Charter defines general decisioning but does not specify DFS 504 lineage decision rights, including who approves CDE changes, system-of-record changes, mapping changes, reconciliation break closure, risk acceptance, or manual workaround extensions. Key source: data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight, and 504.3(d) requires documented remediation of material improvement areas. General committee voting rights do not establish DFS 504-specific accountability.
GL-30 | Control execution evidence is not consistently included | 504.3(a)-(d), 504.4 | The documents describe controls and governance, but the reviewed set does not include complete samples of executed reconciliations, test results, validation reports, issue closures, change approvals, DGC minutes, and management sign-offs. | Controls may be viewed as designed but not proven effective. This creates regulatory defensibility risk for annual certification. | All reviewed documents provide design-level evidence. Operating evidence is limited in the materials reviewed. | Establish a DFS 504 evidence repository and recurring evidence review process. | For TM… This was provided in great detail. Vendor requested Data lineage issue logs and received last action plan. Recommend to provide Vendor with 1.) The PRO Action Plan, and 2.) Current Compliance issues log. For TM… simply ask for additional samples if need. | 18 | 18 | 18 | Support for pushback: The feedback is potentially mitigating for TM if detailed evidence was provided, but it confirms that additional artifacts such as action plans and issue logs should be reviewed. The finding remains open pending review of executed reconciliations, test results, validation reports, issue closures, approvals, DGC minutes, and management sign-offs. Key sources: annual bsa assessment(1).pdf; ofac annual risk assessment.pdf; data governance policy.pdf; changemanagement.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf; data governance committee charter.pdf. DFS basis: 3 NYCRR 504.3(a)-(d) establishes program requirements; 504.4 requires supporting records, schedules, and data to be retained for examination.
GL-31 | CDE-Scoped Issue Tracking Creates Coverage Blind Spots. | 504.3(c)(1)–(3), 504.3(c)(4) | Material data issues impacting transaction monitoring or filtering may not be centrally tracked, reducing visibility and weakening governance and certification support. | The IMR procedure states that only CDE/KDE-related issues are tracked in the centralized Branch Data Issue Log, while other issues may be handled separately, creating fragmented oversight. | The IMR procedure limits centralized issue tracking to confirmed data quality issues related to CDEs/KDEs, with other issues potentially tracked outside the central log. This creates a structural dependency on the completeness of the CDE inventory and excludes broader AML/OFAC data flows from consistent governance. | Expand the centralized Branch Data Issue Log to capture all AML/OFAC?relevant data issues, regardless of whether they relate to formally designated CDEs/KDEs. Update the IMR procedure to require centralized logging of any data issue that impacts transaction monitoring, sanctions filtering, investigations, or regulatory reporting, with CDE/KDE tagging used for prioritization rather than gating inclusion. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported by the IMR Procedure’s scope limitation. If central issue tracking applies only to confirmed CDE/KDE issues, then DFS 504-relevant non-CDE issues or issues arising from incomplete CDE scoping may not be governed centrally. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(1)-(3) requires all relevant data sources and complete/accurate data flows, not only predefined CDEs; 504.3(c)(4) requires governance/management oversight. IMR should capture all AML/OFAC-relevant data integrity issues that could affect TM/filtering.
GL-32 | Explicit Exclusion of Manual Data from Scope. | 504.3(c)(1)–(3), 504.3(c)(4) | Manual processes represent high-risk areas (e.g., payment screening workarounds, reconciliation adjustments, reporting overrides). Excluding them creates a blind spot in DFS 504 control coverage. | The IMR defines scope limitations that exclude manual data processes, which are often critical control points in AML and sanctions workflows. | The IMR procedure excludes manual data processes (e.g., spreadsheets, manual adjustments) from in-scope data elements for issue tracking and governance. | Formally bring manual data processes (e.g., spreadsheets, manual adjustments, overrides, reconciliations) within the scope of the IMR framework. Require identification and documentation of key manual touchpoints supporting AML/OFAC workflows and mandate that related data issues are logged, assessed, and remediated under the same governance standards as system?generated data. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because exclusion of manual data/processes from IMR scope creates a blind spot where manual reconciliations, spreadsheet adjustments, manual screening, or reporting overrides may affect DFS 504 data integrity. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(1)-(3) requires control over relevant data sources and complete/accurate flows, and 504.3(c)(4) requires governance/management oversight. Manual processes are often the highest-risk points in compliance data flows and should be included in issue governance.
GL-33 | Issue Management Not Explicitly Linked to AML/OFAC Systems. | 504.3(a), 504.3(b), 504.3(c)(4) | AML/OFAC-specific data issues may not be prioritized appropriately, reducing the effectiveness of oversight over transaction monitoring and sanctions filtering data integrity. | The IMR procedure describes generic data issue management processes without referencing compliance systems or regulatory data flows. | The IMR framework is designed as an enterprise data governance process and does not explicitly link issue management to key compliance systems such as Prime (TM), FircoSoft (filtering), or RegTechOne (CRR). | Amend the IMR framework to explicitly reference key AML/OFAC systems and data flows (e.g., transaction monitoring, sanctions filtering, CRR). Require issue records to identify the impacted compliance system(s) and downstream controls to ensure AML/OFAC?related issues are visible, prioritized, and escalated in line with regulatory risk. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding remains supported because the IMR Procedure is drafted as a general data governance process and does not explicitly connect issue management to Prime, FircoSoft, RegTechOne, SWIFT/Fedwire, or other AML/OFAC systems. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(a) and 504.3(b) require reasonably designed TM and filtering programs; 504.3(c)(4) requires governance/management oversight. AML/OFAC data issues should be identifiable, prioritized, and escalated based on compliance-system impact.
GL-34 | No DFS 504-Specific Severity and Escalation Triggers. | 504.3(c)(4), 504.3(d) | Critical AML/OFAC data integrity failures may not be escalated in a timely or consistent manner, increasing regulatory and operational risk. | Severity classification criteria are defined in general data quality terms without explicit linkage to AML/OFAC regulatory risk triggers. | The IMR defines severity levels based on impact and data quality attributes but does not include DFS 504-specific escalation triggers such as missed transaction feeds, failed sanctions screening, or reconciliation breaks. | Define DFS 504?specific severity criteria and escalation triggers within the IMR, including explicit examples such as missing transaction feeds, failed sanctions screening, reconciliation breaks, or control bypasses. Align escalation thresholds to regulatory significance and require timely notification to Compliance and senior management for high?impact AML/OFAC issues. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. Disagree with AML reference as 504.3(a) or (d) is not present. Request Vendor to look at all provided PCS Reconciliation Reports and Control Logs. Recommend to discuss the CCBNY Compliance and IT processes in place and Issues Log. | 18 | 18 | 18 | Support for pushback: The finding remains valid even if the AML reference should be refined. PCS reconciliation reports or control logs may evidence operational controls, but they do not show that the IMR severity model includes DFS 504-specific escalation triggers such as missed feeds, failed sanctions screening, unprocessed transactions, material reconciliation breaks, or mapping defects. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance/management oversight and controlled/reported/audited changes; 504.3(d) requires documentation of material improvement areas. Severity criteria should be tailored to TM/filtering risk.
GL-35 | Issue Lifecycle Not Integrated with Change Management. | 504.3(c)(4), 504.3(d) | Data issue remediation may bypass formal change controls, increasing the risk of introducing new defects or breaking existing data lineage. | The IMR lifecycle is defined independently of the Change Management / Testing Methodology, with no explicit requirement to route fixes through controlled change processes. | The IMR defines a lifecycle (identify, assess, remediate, validate, close) but does not explicitly require integration with formal change management processes for system or data fixes. | Integrate the IMR issue lifecycle with formal Change Management and Testing requirements. Require that all data or system remediation actions flow through approved change processes, including impact assessment, testing, approvals, and post?implementation validation, to preserve data lineage integrity and control stability. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because the IMR lifecycle is not explicitly integrated with formal change management, which creates risk that data-fix remediation could bypass change tickets, testing, approvals, regression testing, and post-implementation validation. Key sources: data issue management.pdf; changemanagement.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires policies/procedures governing changes to the TM/filtering program so changes are defined, managed, controlled, reported, and audited; 504.3(d) requires documented remediation efforts. Issue remediation and change control should be linked.
GL-36 | Validation Requirements Lack Independence Criteria. | 504.3(c)(4), 504.3(d) | Issues may be closed without sufficient independent challenge, reducing confidence in remediation effectiveness and audit defensibility. | The IMR references validation and closure but does not define independence standards or roles for validation activities. | The IMR requires validation before issue closure but does not clearly define independent validation requirements, such as separation of duties or independent review by Risk, Audit, or Compliance functions. | Define clear independent validation standards for issue closure, including separation of duties between issue owners and validators. Require validation by an independent function (e.g., Compliance, Risk Management, Internal Audit, or a separate control team) for medium? and high?risk AML/OFAC data issues. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because validation before closure is positive, but the IMR Procedure does not clearly define independence criteria, segregation of duties, or second-line/independent review for material DFS 504 issues. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance and management oversight; 504.3(d) requires documentation of remediation efforts. For high-risk TM/filtering data issues, closure credibility depends on independent validation or challenge.
GL-37 | Issue Trends Not Linked to Model or Scenario Tuning. | 504.3(a)(5), 504.3(b)(3), 504.3(c)(4) | Recurring data issues may not drive systematic improvements in monitoring or filtering effectiveness, increasing the risk of repeated control failures. | The IMR includes root cause analysis but does not connect outputs to model governance or tuning processes described in the Model Governance Guide. | The IMR tracks issues and root causes but does not explicitly require linkage of recurring data issues to transaction monitoring rule tuning, sanctions filtering tuning, or CRR recalibration. | Establish a formal feedback loop between IMR outputs and model governance and tuning processes. Require recurring or systemic AML/OFAC data issues to be reviewed as inputs into transaction monitoring scenario tuning, sanctions filtering adjustments, and CRR recalibration, with documented linkage and accountability. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because the IMR Procedure includes root cause analysis but does not explicitly require issue trends to feed model governance, TM scenario tuning, filtering tuning, or CRR recalibration. Key sources: data issue management.pdf; compliance governance guidepdf.pdf; compliance model gov.pdf. DFS basis: 3 NYCRR 504.3(a)(5) and 504.3(b)(3) require testing/model validation and data input/output review; 504.3(c)(4) requires governance/management oversight. Recurring data issues should drive continuous program improvement.
GL-38 | Data Issue Log Not Defined as DFS 504 Evidence Artifact. | 504.3(c)(4), 504.3(d), 504.4 | The Branch may lack a complete and defensible record of data issues, remediation, and closure for regulatory review and certification support. | The IMR defines issue tracking and logging but does not align the log with DFS 504 certification or evidence retention requirements. | While the IMR establishes a centralized issue log, it does not define the log as part of the DFS 504 certification evidence package, nor does it specify retention or reporting requirements tied to regulatory expectations. | Designate the Branch Data Issue Log as a DFS 504 control evidence artifact. Update documentation to define retention, reporting, and certification support requirements, and ensure the log supports management attestations, internal challenge, and regulatory examination needs. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding remains supported because the IMR Procedure establishes a data issue log, but does not designate the log as a DFS 504 evidence artifact with defined retention and reporting requirements for certification support. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(4) requires governance/management oversight, 504.3(d) requires documentation of material improvement/remediation efforts, and 504.4 requires supporting records, schedules, and data to be maintained for examination. The issue log should be part of the certification evidence package.
GL-39 | “Confirmed Issues Only” Tracking Model Creates Detection Risk. | 504.3(c)(2), 504.3(c)(4) | Early warning signals and potential systemic issues may not be captured or escalated, leading to delayed detection and remediation. | The IMR specifies that confirmed data quality issues are tracked in the central log, which may exclude suspected or emerging issues. | The IMR framework focuses on tracking confirmed data issues, potentially excluding suspected or unverified issues from formal tracking. | Expand the IMR framework to include suspected, emerging, or potential data issues through a formal pre?confirmation or observation status. Require these items to be logged, reviewed, and either escalated or closed based on defined criteria, supporting early detection and proactive risk management. | References DGO'S DG-05-260 Data Issue Management and Remediation (IMR) Procedure.pdf. Please refer to the CCO - Mildred Harper's feedback already provided via email on 05/05/2026 and at the Status Meeting on 05/06/2026. | 18 | 18 | 18 | Support for pushback: The finding is supported because a confirmed-issues-only tracking model can delay visibility into suspected or emerging data integrity issues that may later prove material to TM/filtering completeness or accuracy. Key source: data issue management.pdf. DFS basis: 3 NYCRR 504.3(c)(2) requires validation of integrity, accuracy, and quality of data; 504.3(c)(4) requires governance/management oversight. Suspected issues should be triaged and tracked preliminarily until confirmed, downgraded, or closed.

## Regulation Reference
Reference | Source
3 NYCRR 504.3 - Transaction Monitoring and Filtering Program Requirements | https://www.law.cornell.edu/regulations/new-york/3-NYCRR-504.3
NYDFS Transaction Monitoring Certification (504) guidance | https://www.dfs.ny.gov/industry_guidance/transaction_monitoring
Notes | Supporting evidence column uses the document filenames uploaded in this assessment and the cited DFS 504.3 subsections.